## Master Dashboard
MASTER DASHBOARD — DISTRICT PRIORITY AGENDA REVIEW, LUDHIANA
Auto roll-up ¦ Data as on 05-06-2026 ¦ Cadence: every 3–4 days / before each weekly review
⚙ Auto-Flag Threshold (× Flag-Bar for achievement rules):
| 1 | 1.00 = flag anyone below the Flag-Bar; lower (e.g. 0.90) for stricter.
# | Officer / Tab | Total KPIs | Completed | On Track | In Progress | Pending/Blocked | Not Started | % Done | 🔴 Flags
1 | ADC (G) | 111 | 1 | 10 | 82 | 18 | 0 | 9.91% | 54
2 | ADC (RD) | 71 | 4 | 2 | 44 | 19 | 2 | 8.451% | 36
3 | ADC (UD) | 9 | 0 | 0 | 6 | 3 | 0 | 0% | 2
4 | ADC (J) | 12 | 1 | 0 | 5 | 6 | 0 | 8.333% | 3
5 | ADC (K) | 10 | 0 | 0 | 6 | 4 | 0 | 0% | 5
6 | CMFO | 39 | 0 | 0 | 13 | 26 | 0 | 0% | 20
7 | AC (G) | 30 | 3 | 1 | 18 | 8 | 0 | 13.33% | 11
8 | DRO | 18 | 0 | 0 | 13 | 5 | 0 | 0% | 5
9 | SDM Samrala | 6 | 0 | 0 | 1 | 5 | 0 | 0% | 2
10 | SDM Jagraon | 6 | 0 | 0 | 2 | 4 | 0 | 0% | 1
11 | SDM Payal | 6 | 0 | 0 | 5 | 1 | 0 | 0% | 1
12 | SDM East | 9 | 0 | 0 | 3 | 6 | 0 | 0% | 0
13 | SDM West | 10 | 0 | 0 | 5 | 5 | 0 | 0% | 3
14 | SDM Raikot | 7 | 1 | 0 | 4 | 2 | 0 | 14.29% | 1
15 | RTA | 5 | 0 | 0 | 5 | 0 | 0 | 0% | 0
| DISTRICT TOTAL | 349 | 10 | 13 | 212 | 112 | 2 | 6.59% | 144
WEEKLY MEETING FOCUS
• Each officer tab shows SCHEMES (metrics) first, then PRIORITY TASKS — take highest 🔴 Flags + Pending first.
• Each scheme opens with a 📊 SNAPSHOT band of headline totals.
• Filter any tab's 'Auto-Flag' for 🔴 to list that officer's at-risk items.
• Connect officer workbooks via the 'Data Connections' tab to make figures auto-refresh.

## Instructions
OFFICE OF THE DEPUTY COMMISSIONER-CUM-DISTRICT MAGISTRATE, LUDHIANA
MASTER PRIORITY AGENDA — REVIEW & TRACKING (DC consolidated)
Purpose | DC's consolidated view of all priority agendas. Data is fed up from each officer's own workbook (see 'Data Connections' tab). The DC runs the weekly review from here + the Master Dashboard.
Two-tier design | Each officer maintains their OWN workbook (one tab per scheme + a Priority Tasks tab). Those cells link into this master via IMPORTRANGE. Update once in the officer workbook → flows up here.
Each officer tab is split | ▣ SCHEMES (metric-based) — quantitative agendas with targets, shown FIRST under a blue banner. ▣ PRIORITY TASKS (qualitative) — assigned tasks, shown BELOW under a gold banner.
📊 SNAPSHOT band | Each scheme opens with light-blue bold headline totals (e.g. Rangla P-I: Total/Started/In Progress/Completed/Not Started).
Auto bottom-performer flag | 🔴 LOW (below Flag-Bar) / 🔴 HIGH (above pendency ceiling). Threshold on Master Dashboard B4. Manual override via 'Bottom Performer' column (Auto/Yes/No).
Linking | Until officer workbook URLs are pasted (Data Connections tab), the figures here are the 04–05 Jun headline values. After linking, Current/Status/Flag auto-refresh from each officer workbook.
MLA Works | MLA constituency works remain in the separate linked MLA Works List sheet (unchanged).

## ADC (G)
ADC (G) — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ SCHEMES — metric-based (fed from officer workbook)
1 | MMSBY — Sehat Bima Yojna | 📊 Total cards made — cumulative 26 May–04 Jun |  |  |  |  | 7669 | [7 empty] | District total across all ACs incl. not-mapped (5,917 dept-channel + 1,752 Sewa-Kendra).
|  | 📊 Cards made today — 04 Jun |  |  |  |  | 921 | [7 empty] | All channels combined on 04 Jun (674 dept + 247 Sewa-Kendra).
|  | 📊 Cards NOT mapped to any AC |  |  |  |  | 186 | [7 empty] | Generated but not yet linked to an Assembly Constituency — to be reassigned.
|  | 📊 Nodals yet to fill Phase-18 sheet |  |  |  |  | 6 | [7 empty] | Sahnewal, Payal, Khanna, Dakha, Samrala, Atam Nagar.
|  | Total cards — 04 Jun (single day) | cards |  |  |  | 921 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 674 dept + 247 SK |  | ADCG-001
|  | Total cards — cumulative 26 May–04 Jun | cards |  |  |  | 7669 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 5917 dept + 1752 SK |  | ADCG-002
|  | Channel — DM CSC (04 Jun) | cards |  |  | 832 | 795 | -37 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Prev day 832 — Cards generated via DM-CSC (Common Service Centre) channel that day. |  | ADCG-003
|  | Channel — Dr Cooperation / PACS (04 Jun) | cards |  |  | 18 | 20 | 2 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Cards via Dr Cooperation / PACS societies that day. |  | ADCG-004
|  | Channel — Agriculture Dept (04 Jun) | cards |  |  | 16 | 19 | 3 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Cards via Agriculture Dept that day. |  | ADCG-005
|  | Channel — ASHA cards (04 Jun) | cards |  |  | 511 | 582 | 71 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Sharp drop since 08 May (was 3961 on 28 Apr) — Cards by ASHA workers that day. |  | ADCG-006
|  | Channel — Hospital total (04 Jun) | cards |  |  | 51 | 40 | -11 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Govt 33 / Private 7 — Cards issued at hospitals that day (Govt + Private). |  | ADCG-007
|  | Govt hospital cards (04 Jun) | cards |  |  | 47 | 33 | -14 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Issuance at govt facilities (DH/SDH/AAC) that day. |  | ADCG-008
|  | Private hospital cards (04 Jun) | cards | 20 | 15 | 2 | 7 | 5 | 35% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Private penetration low — Private-hospital issuance that day — low penetration. | MIN | ADCG-009
|  | Not-Mapped cards (to reconcile) | cards |  | 100 |  | 186 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Cumulative not-mapped pool | MAX | ADCG-010
|  | Phase-18 sheet — nodals NOT filled | nodals | 6 | 0 |  | 6 |  | 100% | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Sahnewal, Payal, Khanna, Dakha, Samrala, Atam Nagar | MAX | ADCG-011
|  | Cards — Atam Nagar (04 Jun) | cards | 50 | 50 |  | 25 |  | 50% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 25 cards + 0 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-012
|  | Cards — Dakha (04 Jun) | cards | 50 | 50 |  | 21 |  | 42% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 21 cards + 0 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-013
|  | Cards — Gill (04 Jun) | cards | 50 | 50 |  | 79 |  | 158% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 28 cards + 51 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-014
|  | Cards — Jagraon (04 Jun) | cards | 50 | 50 |  | 117 |  | 234% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 68 cards + 49 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-015
|  | Cards — Khanna (04 Jun) | cards | 50 | 50 |  | 36 |  | 72% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 36 cards + 0 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-016
|  | Cards — Ludhiana Central (04 Jun) | cards | 50 | 50 |  | 89 |  | 178% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 53 cards + 36 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-017
|  | Cards — Ludhiana East (04 Jun) | cards | 50 | 50 |  | 62 |  | 124% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 48 cards + 14 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-018
|  | Cards — Ludhiana North (04 Jun) | cards | 50 | 50 |  | 22 |  | 44% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 19 cards + 3 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-019
|  | Cards — Ludhiana South (04 Jun) | cards | 50 | 50 |  | 15 |  | 30% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 15 cards + 0 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-020
|  | Cards — Ludhiana West (04 Jun) | cards | 50 | 50 |  | 61 |  | 122% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 60 cards + 1 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-021
|  | Cards — Payal (04 Jun) | cards | 50 | 50 |  | 28 |  | 56% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 28 cards + 0 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-022
|  | Cards — Raikot (04 Jun) | cards | 50 | 50 |  | 19 |  | 38% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 19 cards + 0 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-023
|  | Cards — Sahnewal (04 Jun) | cards | 50 | 50 |  | 42 |  | 84% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 34 cards + 8 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-024
|  | Cards — Samrala (04 Jun) | cards | 50 | 50 |  | 119 |  | 238% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 81 cards + 38 SK — Total MMSBY cards in this AC on 04 Jun (incl. Sewa-Kendra). | MIN | ADCG-025
2 | AAC & SDH (Aam Aadmi Clinics / SDH) | 📊 AAC Phase 8/9/10 — total sites |  |  |  |  | 48 | [7 empty] | Inaugurated 17 ¦ Work in progress 30 ¦ Problematic 1.
|  | 📊 SHC→AAC Phase 11 — total sites |  |  |  |  | 32 | [7 empty] | Work orders given 28 ¦ In re-tendering 4 (all PHSC). 8 each across IT/Mandi/Panch Raj/PHSC.
|  | AAC Ph 8/9/10 — inaugurated | sites | 48 | 48 |  | 17 |  | 35.42% | Completed | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | of 48 total | MIN | ADCG-035
|  | AAC Ph 8/9/10 — work in progress | sites |  |  |  | 30 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | ADCG-036
|  | AAC — at >=95% completion | sites |  |  |  | 10 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | ADCG-037
|  | AAC — at 90% completion | sites |  |  |  | 2 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | ADCG-038
|  | AAC — at 80% completion | sites |  |  |  | 4 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | ADCG-039
|  | AAC — at 70% completion | sites |  |  |  | 7 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | ADCG-040
|  | AAC — at 60% completion | sites |  |  |  | 6 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | ADCG-041
|  | AAC — problematic site | sites | 0 | 0 |  | 1 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 |  | MAX | ADCG-042
|  | SHC->AAC Ph 11 — work orders given | sites | 32 | 32 |  | 28 |  | 87.5% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | IT 8 / Mandi 8 / Panch Raj 8 / PHSC 4 | MIN | ADCG-043
|  | SHC->AAC — in re-tendering | sites | 0 | 0 |  | 4 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | All 4 at PHSC: 2 work orders pending at Chief PHSC, 2 cancelled by MD PHSC & re-tendering. Threeke alt site — Sarpanch NOC awaited. | MAX | ADCG-044
3 | Census 2026 — HLB Progress | 📊 Total HLBs (House Listing Blocks) |  |  |  |  | 3778 | [7 empty] | All 3,778 in progress; 0 not started. Completed: 1,408 (37%).
|  | 📊 Census houses — expected vs listed |  |  |  |  | 718019 | [7 empty] | 7,18,019 of 8,59,510 expected houses listed (84%).
|  | District — HLBs completed | HLBs | 3778 | 1889 |  | 1408 |  | 37.27% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | All 3778 in progress; 0 not started | MIN | ADCG-045
|  | District — census houses listed | houses | 859510 | 773559 |  | 718019 |  | 83.54% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 84% against expected | MIN | ADCG-046
|  | HLBs completed — Tehsil Samrala | HLBs | 348 | 174 |  | 196 |  | 56.32% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Houses 61,278/65,019 (94%) | MIN | ADCG-047
|  | HLBs completed — Tehsil Khanna | HLBs | 158 | 79 |  | 135 |  | 85.44% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Houses 32,959/32,579 (101%) | MIN | ADCG-048
|  | HLBs completed — Tehsil Payal | HLBs | 302 | 151 |  | 139 |  | 46.03% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Houses 57,331/64,602 (89%) | MIN | ADCG-049
|  | HLBs completed — Tehsil Ludhiana East | HLBs | 994 | 497 |  | 230 |  | 23.14% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Houses 159,534/211,624 (75%) | MIN | ADCG-050
|  | HLBs completed — Tehsil Ludhiana West | HLBs | 679 | 340 |  | 16 |  | 2.356% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Houses 133,747/189,633 (71%) | MIN | ADCG-051
|  | HLBs completed — Tehsil Raikot | HLBs | 274 | 137 |  | 122 |  | 44.53% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Houses 56,132/60,791 (92%) | MIN | ADCG-052
|  | HLBs completed — Tehsil Jagraon | HLBs | 435 | 218 |  | 278 |  | 63.91% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Houses 91,305/96,859 (94%) | MIN | ADCG-053
|  | HLBs completed — MC Macchhiwara | HLBs | 49 | 24 |  | 33 |  | 67.35% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Houses 11,625/12,156 (96%) | MIN | ADCG-054
|  | HLBs completed — MC Samrala | HLBs | 38 | 19 |  | 30 |  | 78.95% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Houses 9,706/9,628 (101%) | MIN | ADCG-055
|  | HLBs completed — MC Khanna | HLBs | 224 | 112 |  | 125 |  | 55.8% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Houses 37,058/43,958 (84%) | MIN | ADCG-056
|  | HLBs completed — MC Payal | HLBs | 12 | 6 |  | 8 |  | 66.67% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Houses 2,867/2,959 (97%) | MIN | ADCG-057
|  | HLBs completed — MC Maloud | HLBs | 13 | 6 |  | 4 |  | 30.77% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Houses 2,942/3,413 (86%) | MIN | ADCG-058
|  | HLBs completed — MC Doraha | HLBs | 42 | 21 |  | 37 |  | 88.1% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Houses 9,840/9,835 (100%) | MIN | ADCG-059
|  | HLBs completed — MC Sahnewal | HLBs | 45 | 22 |  | 12 |  | 26.67% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Houses 10,360/11,226 (92%) | MIN | ADCG-060
|  | HLBs completed — MC Mullanpur Dakha | HLBs | 39 | 20 |  | 13 |  | 33.33% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Houses 8,503/8,273 (103%) | MIN | ADCG-061
|  | HLBs completed — MC Raikot | HLBs | 39 | 20 |  | 14 |  | 35.9% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Houses 12,701/12,838 (99%) | MIN | ADCG-062
|  | HLBs completed — MC Jagraon | HLBs | 87 | 44 |  | 16 |  | 18.39% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Houses 20,131/24,117 (83%) | MIN | ADCG-063
4 | SIR — Electors Mapped (AC-wise) | 📊 Total electors (district) |  |  |  |  | 2685915 | [7 empty] | Mapped 20,21,328 (75.26%) ¦ Not mapped 6,64,587. 8 ACs below the 75% bar.
|  | 57-Khanna — electors mapped | electors | 174276 | 130707 |  | 134167 |  | 76.99% | On Track |  | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 40,109 (77.0%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-064
|  | 58-Samrala — electors mapped | electors | 176828 | 132621 |  | 154962 |  | 87.63% | On Track |  | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 21,866 (87.6%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-065
|  | 59-Sahnewal — electors mapped | electors | 274011 | 205508 |  | 193740 |  | 70.71% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 80,271 (70.7%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-066
|  | 60-Ludhiana East — electors mapped | electors | 228802 | 171602 |  | 156290 |  | 68.31% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 72,512 (68.3%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-067
|  | 61-Ludhiana South — electors mapped | electors | 183343 | 137507 |  | 109236 |  | 59.58% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 74,107 (59.6%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-068
|  | 62-Atam Nagar — electors mapped | electors | 160607 | 120455 |  | 106731 |  | 66.45% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 53,876 (66.5%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-069
|  | 63-Ludhiana Central — electors mapped | electors | 149728 | 112296 |  | 103728 |  | 69.28% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 46,000 (69.3%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-070
|  | 64-Ludhiana West — electors mapped | electors | 169596 | 127197 |  | 112402 |  | 66.28% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 57,194 (66.3%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-071
|  | 65-Ludhiana North — electors mapped | electors | 203121 | 152341 |  | 142413 |  | 70.11% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 60,708 (70.1%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-072
|  | 66-Gill — electors mapped | electors | 284384 | 213288 |  | 212563 |  | 74.75% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 71,821 (74.8%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-073
|  | 67-Payal — electors mapped | electors | 166556 | 124917 |  | 147687 |  | 88.67% | On Track |  | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 18,869 (88.7%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-074
|  | 68-Dakha — electors mapped | electors | 184119 | 138089 |  | 160838 |  | 87.36% | On Track |  | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 23,281 (87.4%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-075
|  | 69-Raikot — electors mapped | electors | 147891 | 110918 |  | 132789 |  | 89.79% | On Track |  | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 15,102 (89.8%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-076
|  | 70-Jagraon — electors mapped | electors | 182653 | 136990 |  | 153782 |  | 84.19% | On Track |  | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 28,871 (84.2%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-077
|  | District — electors mapped | electors | 2685915 | 2014436 |  | 2021328 |  | 75.26% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 664,587 (75.26%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-078
5 | SIR — EFDIATRIBUTED (AC-wise) | 📊 Total electors (district) |  |  |  |  | 2685915 | [7 empty] | Mapped 20,21,328 (75.26%) ¦ Not mapped 6,64,587. 8 ACs below the 75% bar.
|  | 57-Khanna — electors mapped | electors | 174276 | 130707 |  | 134167 |  | 76.99% | On Track |  | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 40,109 (77.0%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-064
|  | 58-Samrala — electors mapped | electors | 176828 | 132621 |  | 154962 |  | 87.63% | On Track |  | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 21,866 (87.6%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-065
|  | 59-Sahnewal — electors mapped | electors | 274011 | 205508 |  | 193740 |  | 70.71% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 80,271 (70.7%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-066
|  | 60-Ludhiana East — electors mapped | electors | 228802 | 171602 |  | 156290 |  | 68.31% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 72,512 (68.3%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-067
|  | 61-Ludhiana South — electors mapped | electors | 183343 | 137507 |  | 109236 |  | 59.58% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 74,107 (59.6%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-068
|  | 62-Atam Nagar — electors mapped | electors | 160607 | 120455 |  | 106731 |  | 66.45% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 53,876 (66.5%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-069
|  | 63-Ludhiana Central — electors mapped | electors | 149728 | 112296 |  | 103728 |  | 69.28% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 46,000 (69.3%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-070
|  | 64-Ludhiana West — electors mapped | electors | 169596 | 127197 |  | 112402 |  | 66.28% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 57,194 (66.3%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-071
|  | 65-Ludhiana North — electors mapped | electors | 203121 | 152341 |  | 142413 |  | 70.11% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 60,708 (70.1%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-072
|  | 66-Gill — electors mapped | electors | 284384 | 213288 |  | 212563 |  | 74.75% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 71,821 (74.8%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-073
|  | 67-Payal — electors mapped | electors | 166556 | 124917 |  | 147687 |  | 88.67% | On Track |  | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 18,869 (88.7%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-074
|  | 68-Dakha — electors mapped | electors | 184119 | 138089 |  | 160838 |  | 87.36% | On Track |  | Auto | Gov Cell (report) | 05-06-2026 | Not mapped 23,281 (87.4%) — Electors mapped of total in this AC; bar = 75% of total electors. | MIN | ADCG-075
6 | Stubble Burning | 📊 Environmental Compensation cases |  |  |  |  | 93 | [7 empty] | EC imposed Rs 4,90,000 ¦ Red entries 67 ¦ FIRs 1 ¦ Field visits pending 108.
|  | Environmental Compensation — cases | cases |  |  |  | 93 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Total EC imposed Rs 4,90,000 |  | ADCG-094
|  | Red entries (as on 17.05) | entries | 0 | 0 |  | 67 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Raikot & Jagraon flagged | MAX | ADCG-095
|  | FIRs filed | FIRs |  |  |  | 1 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | ADCG-096
|  | Visits pending (of incidents) | visits | 0 | 0 |  | 108 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 |  | MAX | ADCG-097
7 | Revenue — Uncontested Mutation Pendency | 📊 Highest pendency officer |  |  |  |  | 653 | [7 empty] | NT Ludhiana East (653) is the single highest in the district. Target: keep each below 200.
|  | Mutations pending — NT Ludhiana East | cases |  | 200 | 688 | 653 | -35 |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Uncontested mutations pending with this officer; Change = movement since last review. | MAX | ADCG-100
|  | Mutations pending — NT Ludhiana West | cases |  | 200 | 207 | 220 | 13 |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Uncontested mutations pending with this officer; Change = movement since last review. | MAX | ADCG-101
|  | Mutations pending — T Ludhiana West | cases |  | 200 | 175 | 201 | 26 |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Uncontested mutations pending with this officer; Change = movement since last review. | MAX | ADCG-102
|  | Mutations pending — NT Ludhiana South | cases |  | 200 | 180 | 180 | 0 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Uncontested mutations pending with this officer; Change = movement since last review. | MAX | ADCG-103
|  | Mutations pending — T Raikot | cases |  | 200 | 48 | 166 | 118 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Sharp rise +118 — immediate attention — Uncontested mutations pending with this officer; Change = movement since last review. | MAX | ADCG-104
|  | Mutations pending — T Ludhiana South | cases |  | 200 | 123 | 119 | -4 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Uncontested mutations pending with this officer; Change = movement since last review. | MAX | ADCG-105
|  | Mutations pending — NT Sidhwan Bet | cases |  | 200 | 61 | 82 | 21 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Uncontested mutations pending with this officer; Change = movement since last review. | MAX | ADCG-106
|  | Mutations pending — NT-2 Sahnewal | cases |  | 200 | 79 | 69 | -10 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Uncontested mutations pending with this officer; Change = movement since last review. | MAX | ADCG-107
|  | Mutations pending — NT Raikot | cases |  | 200 | 135 | 67 | -68 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Uncontested mutations pending with this officer; Change = movement since last review. | MAX | ADCG-108
|  | Mutations pending — NT Koom Kalan | cases |  | 200 | 44 | 57 | 13 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Uncontested mutations pending with this officer; Change = movement since last review. | MAX | ADCG-109
8 | Revenue — Family Partition & Svamitva GT | Family Partition — pending (district) | cases | 0 | 5 |  | 11 |  |  | In Progress | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Total 16: appr 3, rej 2; Samrala 6, Maloud 4, Jagraon 2; 8 tehsils NIL | MAX | ADCG-110
|  | Svamitva GT pending — T Ludhiana West | cases | 0 | 10 | 23 | 18 | -5 |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 |  | MAX | ADCG-111
|  | Svamitva GT pending — NT Koom Kalan | cases | 0 | 10 | 12 | 12 | 0 |  | In Progress | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | No change | MAX | ADCG-112
|  | Svamitva GT — tehsils with no change ~1.5 months | tehsils | 0 | 0 |  | 4 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Central, Dehlon, Mullanpur Dakha, Maloud | MAX | ADCG-113
▣ PRIORITY TASKS — qualitative / assigned tasks
9 | PSTC — Supervision (owned by AC-G) | Overall resolution % (monitor AC-G) | % | 80% | 80% |  | 63% |  | 78.75% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Execution owned by AC(G). 147 of 233 grievances resolved (63%). See AC(G) workbook → PSTC tab. | MIN | ADCG-026
|  | Bottom departments to escalate | status | [6 empty] | Pending/Blocked |  | Auto |  |  | Rural Dev & Panchayat 24%, PWD 0%, Revenue 0%, Electricity 63% — pursue via AC(G). |  | ADCG-027
|  | Stale grievances (4+ days) — monitor | no. |  | 10 |  |  |  |  | In Progress |  | Auto |  |  | Track weekly through AC(G) feed; ensure ATRs filed. | MAX | ADCG-028
10 | Desilting Sites — NGT / Meowal / Mandala | NGT court case — next hearing date | date | [6 empty] | Pending/Blocked |  | Auto |  |  | Tender done; Forest DFO NOC pending; non-forest not started |  | ADCG-029
|  | Forest DFO NOC received? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Update pending |  | ADCG-030
|  | Drainage proceeds sent to HQ (DRA)? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Flood Review minutes pending |  | ADCG-031
11 | Flood Protection & Embankments | Sasrali Geotubes installed | tubes | 448 | 448 |  | 51 |  | 11.38% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 35% work; 12 tippers running; work closed 23.05 by XEN Mining | MIN | ADCG-032
|  | Rahon Road — pole shifting pending (mtrs) | mtrs | 0 | 0 |  | 3500 |  |  | In Progress | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 3 km done; 4 underpasses done | MAX | ADCG-033
|  | Flood Control Room operational? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | From 11 May |  | ADCG-034
12 | Flood Compensation — Survey & Disbursal | Cases verified & disbursed | cases | [6 empty] | In Progress |  | Auto |  |  | SDM East / XEN Adesh — notice; DMA suspension query |  | ADCG-098
|  | Flood compensation lock — status | status | [6 empty] | Pending/Blocked |  | Auto |  |  | Confirm status |  | ADCG-099
13 | DDMA | DDMA — pending actions | status | [6 empty] | In Progress |  | Auto |  |  | To be populated |  | ADCG-114

## ADC (RD)
ADC (RD) — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ SCHEMES — metric-based (fed from officer workbook)
1 | Mavan Dhiyan Satikar Yojana (MMMDSY) | 📊 Mahila Satkar Sakhis registered |  |  |  |  | 14548 | [7 empty] | of 25,556 target (56.92%, was 55.29%). Remaining 11,008.
|  | 📊 Anganwadi readiness |  |  |  |  | Paint 72.8% ¦ Furniture 100% | [7 empty] | Paintwork 1,810/2,487; chairs/tables/printing 100%. Nodals: BDPO 6/12, MCL 2/14.
|  | Mahila Satkar Sakhis — registered | sakhis | 25556 | 20445 | 14107 | 14548 | 441 | 56.93% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Remaining 11,008 ¦ 56.92% (was 55.29%) | MIN | ADCRD-001
|  | Anganwadi Centres — paintwork done | centres | 2487 | 2238 | 1776 | 1810 | 34 | 72.78% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Remaining 677 ¦ 72.77% (was 71.4%) | MIN | ADCRD-002
|  | Anganwadi Centres — chairs supplied | centres | 2487 | 2487 | 2487 | 2487 | 0 | 100% | Completed |  | Auto | Gov Cell (report) | 05-06-2026 | 100% | MIN | ADCRD-003
|  | Anganwadi Centres — tables supplied | centres | 2487 | 2487 | 2487 | 2487 | 0 | 100% | Completed |  | Auto | Gov Cell (report) | 05-06-2026 | 100% | MIN | ADCRD-004
|  | Anganwadi Centres — printing material | centres | 2487 | 2487 | 2487 | 2487 | 0 | 100% | Completed |  | Auto | Gov Cell (report) | 05-06-2026 | 100% | MIN | ADCRD-005
|  | BDPO Nodals appointed | nodals | 12 | 12 | 0 | 6 | 6 | 50% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 50% (was 0%) | MIN | ADCRD-006
|  | MCL Nodals appointed | nodals | 14 | 14 | 2 | 2 | 0 | 14.29% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 14.2% — stalled | MIN | ADCRD-007
2 | Rangla Punjab — Phase I | 📊 Total works proposed |  |  |  |  | 433 | [7 empty] | District total, Phase I. Sanctioned amount Rs 34.99 Cr.
|  | 📊 Works started |  |  |  |  | 431 | [7 empty] | 431 of 433 started (Total − Not started).
|  | 📊 Works in progress |  |  |  |  | 326 | [7 empty] | Currently under execution.
|  | 📊 Works completed |  |  |  |  | 105 | [7 empty] | Physically complete.
|  | 📊 Works NOT started |  |  |  |  | 2 | [7 empty] | DD Animal Husbandry (1) + XEN Prov. Divn B&R (1).
|  | Phase I — works completed (district) | works | 433 | 433 |  | 105 |  | 24.25% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 326 in progress; 2 not started | MIN | ADCRD-008
|  | P-I completed — BDPO Doraha | works | 34 | 1 |  | 29 |  | 85.29% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | of 34 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-009
|  | P-I completed — BDPO Jagraon | works | 42 | 1 |  | 4 |  | 9.524% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | of 42 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-010
|  | P-I completed — BDPO Khanna | works | 26 | 1 |  | 0 |  | 0% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | of 26 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-011
|  | P-I completed — BDPO Ludhiana One | works | 76 | 1 |  | 0 |  | 0% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | of 76 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-012
|  | P-I completed — BDPO Ludhiana Two | works | 48 | 1 |  | 1 |  | 2.083% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | of 48 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-013
|  | P-I completed — BDPO Maloud | works | 33 | 1 |  | 19 |  | 57.58% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | of 33 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-014
|  | P-I completed — BDPO Raikot | works | 21 | 1 |  | 21 |  | 100% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | of 21 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-015
|  | P-I completed — BDPO Samrala | works | 34 | 1 |  | 17 |  | 50% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | of 34 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-016
|  | P-I completed — BDPO Sidhwan Bet | works | 24 | 1 |  | 10 |  | 41.67% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | of 24 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-017
|  | P-I completed — BDPO Sudhar | works | 27 | 1 |  | 0 |  | 0% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | of 27 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-018
|  | P-I completed — BDPO Pakhowal | works | 13 | 1 |  | 1 |  | 7.692% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | of 13 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-019
|  | P-I completed — MCL | works | 39 | 1 |  | 0 |  | 0% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | of 39 proposed — Phase-I works physically completed by this agency of its proposed total. | MIN | ADCRD-020
3 | Rangla Punjab — Phase II | 📊 Total works proposed |  |  |  |  | 400 | [7 empty] | District total, Phase II. Sanctioned amount Rs 31.79 Cr.
|  | 📊 Works started |  |  |  |  | 90 | [7 empty] | 90 of 400 started (Total − Not started).
|  | 📊 Works in progress |  |  |  |  | 79 | [7 empty] | Currently under execution.
|  | 📊 Works completed |  |  |  |  | 11 | [7 empty] | Physically complete.
|  | 📊 Works NOT started |  |  |  |  | 310 | [7 empty] | All to begin by 5 June. Largest: MCL 73, Jagraon 43, Dehlon 30, Khanna 28.
|  | Phase II — works completed (district) | works | 400 | 400 |  | 11 |  | 2.75% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 79 in progress; 310 NOT started | MIN | ADCRD-021
|  | Phase II — works NOT started (district) | works | 0 | 0 |  | 310 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | To start by 5 Jun | MAX | ADCRD-022
|  | P-II not started — MCL | works | 0 | 20 |  | 73 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | of 73 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-023
|  | P-II not started — BDPO Jagraon | works | 0 | 20 |  | 43 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | of 44 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-024
|  | P-II not started — BDPO Khanna | works | 0 | 20 |  | 28 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | of 28 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-025
|  | P-II not started — BDPO Dehlon | works | 0 | 20 |  | 30 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | of 30 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-026
|  | P-II not started — BDPO Ludhiana One | works | 0 | 20 |  | 21 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | of 21 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-027
|  | P-II not started — BDPO Doraha | works | 0 | 20 |  | 19 |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | of 43 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-028
|  | P-II not started — BDPO Samrala | works | 0 | 20 |  | 19 |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | of 19 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-029
|  | P-II not started — BDPO Maloud | works | 0 | 20 |  | 16 |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | of 19 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-030
|  | P-II not started — BDPO Ludhiana Two | works | 0 | 20 |  | 47 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | of 48 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-031
|  | P-II not started — BDPO Machhiwara | works | 0 | 20 |  | 4 |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | of 33 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-032
|  | P-II not started — EONC Khanna | works | 0 | 20 |  | 3 |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | of 3 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-033
|  | P-II not started — EONC Raikot | works | 0 | 20 |  | 6 |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | of 7 proposed — Phase-II works not yet started by this agency of its proposed total. | MAX | ADCRD-034
4 | Mission Chardi Kalan | 📊 Schools |  |  |  |  | 9 proj ¦ tender 9 ¦ started 9 ¦ done 0 | [7 empty] | Civil structure almost complete; UC & post-work photos pending from DEO.
|  | 📊 Hospitals |  |  |  |  | 6 proj ¦ tender 4 ¦ started 0 ¦ done 0 | [7 empty] | 2 tenders pending; 2 file-approved on portal; 2 estimates pending from XEN. PWD Kanech tender pending.
|  | Schools — tender done | proj | 9 | 9 |  | 9 |  | 100% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 9 projects; work started 9 | MIN | ADCRD-035
|  | Schools — work completed | proj | 9 | 9 |  | 0 |  | 0% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | UC submitted 0; civil almost done | MIN | ADCRD-036
|  | Hospitals — tender done | proj | 6 | 6 |  | 4 |  | 66.67% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 6 projects | MIN | ADCRD-037
|  | Hospitals — work started | proj | 6 | 6 |  | 0 |  | 0% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | PWD Kanech tender pending | MIN | ADCRD-038
5 | Meri Yogyata Meri Pehchan | Applications received | apps |  |  |  | 1544 |  |  | Not Started |  | Auto | Gov Cell (report) | 05-06-2026 | 291 name boards ready for installation |  | ADCRD-040
|  | Installations done | no. | 1544 | 772 |  | 291 |  | 18.85% | Not Started | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Pilot village planned; Rs8L budget | MIN | ADCRD-041
6 | Dengue & Vector Borne Disease | 📊 Houses visited (district) |  |  |  |  | 34565 | [7 empty] | Containers checked 66,456 ¦ Positive 13 ¦ Breeding-in-houses 11 ¦ Challans 15 ¦ Camps 206.
|  | Houses visited (district) | houses |  |  |  | 34565 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Block-wise survey |  | ADCRD-042
|  | Containers checked | no. |  |  |  | 66456 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | ADCRD-043
|  | Positive containers | no. | 0 | 0 |  | 13 |  |  | In Progress | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 |  | MAX | ADCRD-044
|  | Breeding found in houses | cases | 0 | 0 |  | 11 |  |  | In Progress | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 |  | MAX | ADCRD-045
|  | Challans issued (health) | no. |  |  |  | 15 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | ADCRD-046
|  | Camps organised | no. |  |  |  | 206 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | ADCRD-047
|  | Block: Raikot — houses visited | houses | 500 | 200 |  | 0 |  | 0% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Zero activity — flag | MIN | ADCRD-048
|  | Block: Khanna — houses visited | houses | 500 | 200 |  | 256 |  | 51.2% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  | MIN | ADCRD-049
|  | Block: Dehlon — houses visited | houses | 500 | 200 |  | 314 |  | 62.8% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  | MIN | ADCRD-050
|  | Medicine stock adequate? (Y/N) | Y/N | [6 empty] | On Track |  | Auto |  |  | SDP kit demand raised to Director MOHFW |  | ADCRD-051
7 | Parks, Playgrounds & Anganwadis | Anganwadi Centres — completed | centres | 87 | 87 |  | 87 |  | 100% | Completed |  | Auto | Gov Cell (report) | 05-06-2026 | 100% | MIN | ADCRD-052
|  | Playgrounds Phase 2 — ready for inauguration | grounds |  |  |  | 12 |  |  | On Track |  | Auto | Gov Cell (report) | 05-06-2026 | Phase-1: 8 handed over 04.05 |  | ADCRD-053
|  | Parks Phase 2 (of 100) initiated? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | JC Vineet Rs5 Cr proposal |  | ADCRD-054
8 | Socio-Economic Drug Census | 📊 Survey completed (district) |  |  |  |  | 72079 | [7 empty] | of 7,31,750 target (9.9%). Active supervisors 137; enumerators 998.
|  | Survey — completed (district) | houses | 731750 | 73175 |  | 72079 |  | 9.85% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 9.9% ¦ active supervisors 137; enumerators 998 | MIN | ADCRD-057
|  | Survey completed — Jagraon | houses | 48500 | 4850 |  | 3417 |  | 7.045% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 7.0% of 48,500 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-058
|  | Survey completed — Dakha | houses | 54250 | 5425 |  | 12345 |  | 22.76% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 22.8% of 54,250 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-059
|  | Survey completed — Raikot | houses | 47000 | 4700 |  | 11686 |  | 24.86% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 24.9% of 47,000 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-060
|  | Survey completed — Gill | houses | 74500 | 7450 |  | 13633 |  | 18.3% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 18.3% of 74,500 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-061
|  | Survey completed — Ldh-East | houses | 55500 | 5550 |  | 708 |  | 1.276% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 1.3% of 55,500 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-062
|  | Survey completed — Sahnewal | houses | 69750 | 6975 |  | 2425 |  | 3.477% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 3.5% of 69,750 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-063
|  | Survey completed — Samrala | houses | 54500 | 5450 |  | 4706 |  | 8.635% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 8.6% of 54,500 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-064
|  | Survey completed — Khanna | houses | 48000 | 4800 |  | 4405 |  | 9.177% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 9.2% of 48,000 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-065
|  | Survey completed — Payal | houses | 51750 | 5175 |  | 13952 |  | 26.96% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 27.0% of 51,750 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-066
|  | Survey completed — Ldh-South | houses | 43500 | 4350 |  | 199 |  | 0.4575% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 0.5% of 43,500 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-067
|  | Survey completed — Ldh-Central | houses | 44500 | 4450 |  | 465 |  | 1.045% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 1.0% of 44,500 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-068
|  | Survey completed — Ldh-West | houses | 48000 | 4800 |  | 288 |  | 0.6% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 0.6% of 48,000 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-069
|  | Survey completed — Ldh-North | houses | 50250 | 5025 |  | 164 |  | 0.3264% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 0.3% of 50,250 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-070
|  | Survey completed — Atam Nagar | houses | 41750 | 4175 |  | 3686 |  | 8.829% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 8.8% of 41,750 — Drug-census houses surveyed of this assembly's target. | MIN | ADCRD-071
▣ PRIORITY TASKS — qualitative / assigned tasks
9 | Punjab Nirman | Status update / UCs from BDPOs | status | [6 empty] | In Progress |  | Auto |  |  | Pending |  | ADCRD-039
10 | Dhanasu / Gow Shala | Dhanasu — amount released (of Rs18L) | Rs lakh | 18 | 18 |  | 10 |  | 55.56% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Rs2.74L sanctioned further | MIN | ADCRD-055
|  | Gow Shala Mar-26 payment (Rs15.47L) released? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | To be released by MCL |  | ADCRD-056

## ADC (UD)
ADC (UD) — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ PRIORITY TASKS — qualitative / assigned tasks
1 | MM Tirath Yatra Yojana | Bills pending (count) | bills |  |  |  | 0 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Cleared till 04 May 2026; none pending |  | ADCUD-001
|  | All bills up to date cleared? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  |  |  | ADCUD-002
2 | Buddha Dariya — NGT / Dairies / CBG | Dairies identified (Rajpur/Haibowal) | no. |  |  |  | 6 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Disconnection done; MCL direction passed |  | ADCUD-003
|  | Tajpur — dairies disconnected | no. | 21 | 21 |  | 16 |  | 76.19% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 21 dairies out of complex | MIN | ADCUD-004
|  | CBG plant — site identified? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Jamalpur dump site found for carcass |  | ADCUD-005
|  | CETP/STP — ATR report submitted? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | STP under construction at MC Raikot |  | ADCUD-006
3 | WTP — Water Treatment Plant | WTPs with NO land available | sites | 0 | 0 |  | 3 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | MC Doraha, Maloud, Sahnewal | MAX | ADCUD-007
|  | Mullanpur Dakha — completion status | status | [6 empty] | In Progress |  | Auto |  |  | Priority; Council land pending |  | ADCUD-008
4 | IT / MC Land Price Fixation | Price Fixation Committee meeting held? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | IT case under process |  | ADCUD-009

## ADC (J)
ADC (J) — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ PRIORITY TASKS — qualitative / assigned tasks
1 | YnV Bills | Phase I bills — status | bills | [6 empty] | In Progress |  | Auto |  |  | Phase 1 complete; Phase 2 mtg 5/6 Jun |  | ADCJ-001
|  | Phase III — E-rickshaws on road | no. | 4 | 4 |  | 4 |  | 100% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Campaign started 8 May | MIN | ADCJ-002
|  | SAARC Knit & PP bills mismatch — meeting held? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  |  |  | ADCJ-003
2 | Halwara Airport | 📊 Infrastructure works completed |  |  |  |  | 7 | [7 empty] | of 38 total; 31 ongoing. Operational target was 15 May; electricity damage noted.
|  | Infrastructure works — completed | works | 38 | 38 |  | 7 |  | 18.42% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 31 ongoing; target 20 May | MIN | ADCJ-004
|  | Security accommodation — done? (Y/N) | Y/N |  |  |  | Completed |  |  | Completed |  | Auto | Gov Cell (report) | 05-06-2026 | Training of personnel ongoing |  | ADCJ-005
|  | LIAL — VC held? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  |  |  | ADCJ-006
3 | Flood Protection — Bet Area | Bet area desilting — tenders failed | no. | 0 | 0 |  | 3 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 8 kila; next date 22 May | MAX | ADCJ-007
|  | Khaira Bet — forest objections | no. | 0 | 0 |  | 8 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Forest land; meeting 4 Jun | MAX | ADCJ-008
|  | DDMA flood equipment (Rs5L Red Cross) — tender floated? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | XEN Kamaljit specs; whole district |  | ADCJ-009
4 | Desilting — Khaira Bet Coordination | Escalation to Central Govt / WRD — status | status | [6 empty] | Pending/Blocked |  | Auto |  |  | NGT next date pending |  | ADCJ-010
5 | SPCA | CAPEX funds plan prepared? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | ADC Jagraon recommendation pending |  | ADCJ-011
6 | Raikot Master Plan | Master Plan — status | status | [6 empty] | In Progress |  | Auto |  |  | Update pending |  | ADCJ-012

## ADC (K)
ADC (K) — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ PRIORITY TASKS — qualitative / assigned tasks
1 | Court Cases & Legal Matters | Hadon Bet (YnV) — CM Relief Fund status | status | [6 empty] | Pending/Blocked |  | Auto |  |  | Due 13 May — overdue |  | ADCK-001
|  | No-representation defaults | no. | 0 | 0 |  |  |  |  | In Progress |  | Auto |  |  | Zero tolerance | MAX | ADCK-002
2 | Flood Protection — Sasrali | 📊 Sasrali geotubes installed |  |  |  |  | 51 | [7 empty] | of 448 (35%). Work closed 23.05 by XEN Mining; Show-Cause issued. 12 tippers running.
|  | Sasrali geotubes installed | tubes | 448 | 448 |  | 51 |  | 11.38% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 35% done; closed 23.05 by XEN Mining; SCN issued | MIN | ADCK-003
3 | Flood Protection — Dhulewal | 📊 Dhulewal flood works completed |  |  |  |  | 2 | [7 empty] | of 18 sanctioned; 16 halted (NREGA payment stopped). Rs 97.93L budget decision pending with DC.
|  | Dhulewal works completed | works | 18 | 18 |  | 2 |  | 11.11% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 16 halted; Rs97.93L budget pending DC; SDRF/DMF decision | MIN | ADCK-004
4 | Desilting — Coordination | Working desilting sites | sites | 1 | 1 |  | 0 |  | 0% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Mandala (road denied) & Dopana (forest) — no site working | MIN | ADCK-005
5 | FCI Silage Works | Ghudani Khurd — status | status | [6 empty] | In Progress |  | Auto |  |  | Panchayat not ready; ADC mtg 5 Jun |  | ADCK-006
6 | NHAI — Pkg 2 (Ldh-Ropar) | Possession pending (km) | km | 0 | 0 |  | 5 |  |  | In Progress | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 5.3 of 47.24 km; HC challenge | MAX | ADCK-007
7 | Rahon Road | Road pending (mtrs) | mtrs | 0 | 0 |  | 3500 |  |  | In Progress | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 3 km done; 4 underpasses done; sewerage work | MAX | ADCK-008
8 | SIR (ADC-K) | SIR training — status | status | [6 empty] | In Progress |  | Auto |  |  | Master trainers geared up |  | ADCK-009
9 | Revenue Meeting | Pending revenue actions | status | [6 empty] | In Progress |  | Auto |  |  | Court cases via Sukhpal Ji (ADC-G office) |  | ADCK-010

## CMFO
CMFO — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ SCHEMES — metric-based (fed from officer workbook)
1 | eSewa Pendency & PGRS | 📊 Ludhiana applications received (year) |  |  |  |  | 721312 | [7 empty] | In process 39,539 ¦ Pendency 5.48% of received. Figures below are 05 Jun (Last = 04 Jun).
|  | District — applications in process | apps | 0 | 20000 |  | 39539 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Ludhiana total received 721,312; pendency 5.48% | MAX | CMFO-006
|  | District — pendency % of received | % | 5% | 5% |  | 5.48% |  | 109.6% | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | State comparison rank | MAX | CMFO-007
|  | Pendency — Akash Garg, EOMC MC Ludhiana | apps |  | 1000 | 7700 | 7932 | 232 |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 04 Jun: 7,700 — Applications pending disposal with this officer on the eSewa portal (Current = 05 Jun, Last = 04 Jun). | MAX | CMFO-008
|  | Pendency — Beant Kaur, Clerk CMO | apps |  | 1000 | 5892 | 6634 | 742 |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 04 Jun: 5,892 — Applications pending disposal with this officer on the eSewa portal (Current = 05 Jun, Last = 04 Jun). | MAX | CMFO-009
|  | Pendency — Sukhvir Kaur, Clerk Ldh West | apps |  | 1000 | 5747 | 5579 | -168 |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 04 Jun: 5,747 — Applications pending disposal with this officer on the eSewa portal (Current = 05 Jun, Last = 04 Jun). | MAX | CMFO-010
|  | Pendency — Kuldeep Singh, Clerk Ldh East | apps |  | 1000 | 5168 | 5220 | 52 |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 04 Jun: 5,168 — Applications pending disposal with this officer on the eSewa portal (Current = 05 Jun, Last = 04 Jun). | MAX | CMFO-011
|  | Pendency — Harminder Singh, Tehsildar Ldh West | apps |  | 500 | 2258 | 2505 | 247 |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 04 Jun: 2,258 — Applications pending disposal with this officer on the eSewa portal (Current = 05 Jun, Last = 04 Jun). | MAX | CMFO-012
|  | Pendency — Ranjeet Singh, Tehsildar Ldh East | apps |  | 500 | 542 | 416 | -126 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 04 Jun: 542 — Applications pending disposal with this officer on the eSewa portal (Current = 05 Jun, Last = 04 Jun). | MAX | CMFO-013
|  | Pendency — Gurucharan Singh, Tehsildar Khanna | apps |  | 500 | 260 | 337 | 77 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 04 Jun: 260 — Applications pending disposal with this officer on the eSewa portal (Current = 05 Jun, Last = 04 Jun). | MAX | CMFO-014
|  | Approving authority — ADR Harpreet Singh (overall eSewa) | apps |  | 3000 |  | 6674 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 |  | MAX | CMFO-015
2 | Human Rights Commission (HRC) | 📊 Active HRC cases |  |  |  |  | 13 | [7 empty] | Sent to Commission 3 ¦ Report received (to put up) 2 ¦ Direct reply 4 ¦ Report pending from depts 3 ¦ Transferred out 1.
|  | Total active cases | cases |  |  |  | 13 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 3 sent to Comm; 2 report recd; 4 direct reply; 3 dept pending; 1 transferred |  | CMFO-016
|  | Reports pending from departments | cases | 0 | 0 |  | 3 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | See case rows below | MAX | CMFO-017
|  | Case 204/10/2026 Umesh Narain | case |  |  |  | REPORT PENDING |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with PD NHAI; due 15.06.2026 |  | CMFO-018
|  | Case 3846/10/2026 Grain Market | case |  |  |  | REPORT PENDING |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with CP Ludhiana + MCL; due 22.06.2026 |  | CMFO-019
|  | Case 4832/10/2026 Baldev Singh | case |  |  |  | REPORT PENDING |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with SDM Samrala; due 26.06.2026 |  | CMFO-020
|  | Case 5334/10/2024 Manjit Kaur | case |  |  |  | DIRECT REPLY |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with CP Ludhiana; due 26.06.2026 |  | CMFO-021
|  | Case 2105/10/2026 Arvind | case |  |  |  | DIRECT REPLY |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with Civil Surgeon; due 03.06.2026 |  | CMFO-022
|  | Case 276/1/2026 Umesh Narain | case |  |  |  | SENT TO COMM |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with SDM East (sent to Comm); due 12.06.2026 |  | CMFO-023
3 | NRI Commission | 📊 Active NRI cases |  |  |  |  | 7 | [7 empty] | ATR overdue: 1 (Case 5457/2025, pending SDM Ludhiana West).
|  | Total active NRI cases | cases |  |  |  | 7 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | CMFO-024
|  | Case 5457/2025 Gurcharan Singh | case |  |  |  | ATR OVERDUE |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with SDM Ludhiana West; next 26.05.2026 |  | CMFO-025
|  | Case 4111/2022 Jaspal Singh | case |  |  |  | Final disposal outstanding |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with SDM Jagraon; next 24.09.2026 |  | CMFO-026
|  | Case 2803/2017 Manjeet Singh | case |  |  |  | Reminder issued 18.05 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with SK Branch DC Office; next 22.05.2026 |  | CMFO-027
|  | Case 5311/2024 Rajinder Kaur | case |  |  |  | Letter to SDM Raikot |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with PSC NRI Chandigarh; next 10.07.2026 |  | CMFO-028
|  | Case 3542687 Davinder Grewal | case |  |  |  | Letter to SDM East |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with Commissioner of Police; next 13.05.2026 |  | CMFO-029
|  | Case E540370 Naginder Kaur | case |  |  |  | Letter to SDM East |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Pending with PSC NRI Chandigarh; next 07.05.2024 |  | CMFO-030
4 | Caste Certificate eSewa Pendency | 📊 Total caste-certificate pendency |  |  |  |  | 20093 | [7 empty] | SC 15,847 ¦ OBC/BC 4,050 ¦ General 196. Pending on eSewa with revenue authorities.
|  | Total caste cert pendency | apps | 0 | 5000 |  | 20093 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | SC 15847 + OBC/BC 4050 + General 196 | MAX | CMFO-031
|  | SC certificates pending | apps | 0 | 3000 |  | 15847 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Caste-certificate applications pending on eSewa. | MAX | CMFO-032
|  | OBC/BC certificates pending | apps | 0 | 1000 |  | 4050 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Caste-certificate applications pending on eSewa. | MAX | CMFO-033
|  | Pending — Tehsildar Ldh West (SC) | apps | 0 | 1000 |  | 6519 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Caste-certificate applications pending with this authority on eSewa. | MAX | CMFO-034
|  | Pending — Tehsildar Ldh East (SC) | apps | 0 | 1000 |  | 4684 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Caste-certificate applications pending with this authority on eSewa. | MAX | CMFO-035
|  | Pending — Tehsildar Khanna (SC) | apps | 0 | 1000 |  | 1507 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Caste-certificate applications pending with this authority on eSewa. | MAX | CMFO-036
|  | Pending — Tehsildar Ldh East (OBC/BC) | apps | 0 | 1000 |  | 1670 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Caste-certificate applications pending with this authority on eSewa. | MAX | CMFO-037
|  | Pending — NT Ldh West (OBC/BC) | apps | 0 | 1000 |  | 1335 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Caste-certificate applications pending with this authority on eSewa. | MAX | CMFO-038
▣ PRIORITY TASKS — qualitative / assigned tasks
5 | Southern Bypass — Land Acquisition & Payment | Award revised Rs75Cr->Rs70Cr documented? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | From 11 May |  | CMFO-001
|  | Villages — possession pending | villages | 0 | 0 |  | 16 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | All 16 villages | MAX | CMFO-002
|  | 3.6 km disbursement | status | [6 empty] | Pending/Blocked |  | Auto |  |  | PENDING |  | CMFO-003
6 | Ludhiana–Ropar Package I & II | Package I — amount pending (Rs Cr) | Rs Cr | 0 | 0 |  | 28 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Talwandi Kalan; 3G-1 segment | MAX | CMFO-004
|  | Package II — possession pending (km) | km | 0 | 0 |  | 5 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 5.315 km; arbitration; PD reply overdue | MAX | CMFO-005
7 | Census 2026 (Asst. Nodal) | Control room infra set up? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Training 13 May–13 Jun |  | CMFO-039

## AC (G)
AC (G) — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ SCHEMES — metric-based (fed from officer workbook)
1 | Punjab State Trader Commission (PSTC) | 📊 Total grievances |  |  |  |  | 233 | [7 empty] | All grievances received under PSTC across departments.
|  | 📊 Final resolved |  |  |  |  | 147 | [7 empty] | 63% of total. Implementation under process: 60; Not-agree: 5; Not-resolvable: 7.
|  | MCL — resolved | cases | 52 | 41.6 |  | 45 |  | 86.54% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 87% done ¦ active 7 ¦ 6 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-001
|  | Electricity (PSPCL) — resolved | cases | 40 | 32 |  | 25 |  | 62.5% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 63% done ¦ active 15 ¦ 10 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-002
|  | Local Govt — resolved | cases | 27 | 21.6 |  | 18 |  | 66.67% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 67% done ¦ active 9 ¦ 9 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-003
|  | Others — resolved | cases | 21 | 16.8 |  | 14 |  | 66.67% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 67% done ¦ active 7 ¦ 6 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-004
|  | Rural Dev & Panchayat — resolved | cases | 17 | 13.6 |  | 4 |  | 23.53% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 24% done ¦ active 13 ¦ 11 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-005
|  | Police — resolved | cases | 44 | 35.2 |  | 43 |  | 97.73% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 98% done ¦ active 1 ¦ 1 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-006
|  | District Food & Supply — resolved | cases | 2 | 1.6 |  | 2 |  | 100% | Completed |  | Auto | Gov Cell (report) | 05-06-2026 | 100% done ¦ active 0 ¦ 0 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-007
|  | PWD — resolved | cases | 4 | 3.2 |  | 0 |  | 0% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 0% done ¦ active 4 ¦ 4 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-008
|  | Tax & Excise — resolved | cases | 5 | 4 |  | 4 |  | 80% | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 80% done ¦ active 1 ¦ 0 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-009
|  | Revenue — resolved | cases | 0 |  |  | 0 |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | 0% done ¦ active 0 ¦ 0 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-010
|  | Mandi Board — resolved | cases | 2 | 1.6 |  | 2 |  | 100% | Completed |  | Auto | Gov Cell (report) | 05-06-2026 | 100% done ¦ active 0 ¦ 0 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-011
|  | Pollution Control — resolved | cases | 1 | 0.8 |  | 1 |  | 100% | Completed |  | Auto | Gov Cell (report) | 05-06-2026 | 100% done ¦ active 0 ¦ 0 stale — Resolved of total received for this dept; active = open + under-implementation. | MIN | ACG-012
|  | Total grievances (district) | cases |  |  |  | 233 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Resolved 147; under impl 60; not-agree 5; not-resolvable 7 |  | ACG-013
|  | % resolved — BDPO Ludhiana-1 | % | 80% | 80% |  | 0% |  | 0% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 0 of 5 grievances resolved; 5 stale (4+ days no update). Actor to be called for review. | MIN | ACG-014
|  | % resolved — BDPO Payal | % | 80% | 80% |  | 0% |  | 0% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 0 of 1 grievances resolved; 1 stale (4+ days no update). Actor to be called for review. | MIN | ACG-015
|  | % resolved — BDPO Khanna | % | 80% | 80% |  | 25% |  | 31.25% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 1 of 4 grievances resolved; 3 stale (4+ days no update). Actor to be called for review. | MIN | ACG-016
|  | % resolved — BDPO Dehlon | % | 80% | 80% |  | 33% |  | 41.25% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 2 of 6 grievances resolved; 2 stale (4+ days no update). Actor to be called for review. | MIN | ACG-017
|  | % resolved — EO Jagraon | % | 80% | 80% |  | 50% |  | 62.5% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 4 of 8 grievances resolved; 3 stale (4+ days no update). Actor to be called for review. | MIN | ACG-018
|  | % resolved — PSPCL XEN Ludhiana Central | % | 80% | 80% |  | 50% |  | 62.5% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 5 of 10 grievances resolved; 4 stale (4+ days no update). Actor to be called for review. | MIN | ACG-019
2 | Dormant Accounts & Financial Bills | 📊 Total dormant funds to reconcile |  |  |  |  | 113.5 | [7 empty] | Rs 1.13 Cr across LAC 32L, DC Office 36L, ADC-G 28L, DEO 13L, Tehsil West 4.5L. Welfare Society file with DC.
|  | Total dormant funds to reconcile (Rs L) | Rs lakh |  |  |  | 113.5 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Welfare Society file put up to DC |  | ACG-020
|  | LAC — reconciled? (Rs32L) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Welfare Society creation in progress |  | ACG-021
|  | Tehsil West — reconciled? (Rs4.5L) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Welfare Society creation in progress |  | ACG-022
|  | DC Office — reconciled? (Rs36L) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Welfare Society creation in progress |  | ACG-023
|  | ADC G — reconciled? (Rs28L) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Welfare Society creation in progress |  | ACG-024
|  | DEO — reconciled? (Rs13L) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Welfare Society creation in progress |  | ACG-025
▣ PRIORITY TASKS — qualitative / assigned tasks
3 | Red Cross FD | FDs merged / interest mode | status | [6 empty] | On Track |  | Auto |  |  | 6 FDs merged to 2; monthly interest from June |  | ACG-026
4 | YnV Bills — Phase I & II | SAARC Knit & PP mismatch — meeting held? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Phase 1 complete; Phase 2 mtg 5/6 Jun |  | ACG-027
5 | Court — Raikot Judicial Complex | Letter to D&S Judge — reply received? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Rs7 Cr for judicial infra land |  | ACG-028
6 | Building Committee | Tree felling (multi-level parking) — application filed? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | 147 trees; application filed 17/05 |  | ACG-029
7 | Camera Court Complex — Smart City | Installation % complete | % | 100% | 100% |  |  |  |  | In Progress |  | Auto |  |  | Smart City funds status pending | MIN | ACG-030

## DRO
DRO — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ SCHEMES — metric-based (fed from officer workbook)
1 | Svamitva — Abadi Deh (Urban Property Cards) | Map-1 estates being finalised | estates |  |  |  | 3 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Haibowal Kalan, Jawaddi Khurd, Ayali Khurd |  | DRO-001
|  | Map-2 awaited from SOI | estates | 0 | 0 |  | 4 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Dugri, Rajpura, Barewal Awana, Sunet | MAX | DRO-002
|  | Ground Truthing sent to SOI | estates |  |  |  | 8 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  |  | DRO-003
|  | Ground Truthing PENDING | estates | 0 | 0 |  | 5 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Dhandari Kalan, Noorwala, Kulewal, Jamalpur Awana, Ludhiana City | MAX | DRO-004
|  | Estates with No Laal Lakir | estates |  |  |  | 3 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Karabara, Mahal Bhagat, Phamra |  | DRO-005
2 | Svamitva — Rural Ground Truthing Pendency | 📊 Tehsils with NO change ~1.5 months |  |  |  |  | 4 | [7 empty] | Ludhiana Central, Dehlon, Mullanpur Dakha, Maloud — immediate follow-up needed.
|  | GT pending — T Ludhiana West | cases | 0 | 5 | 23 | 18 | -5 |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 |  | MAX | DRO-006
|  | GT pending — NT Koom Kalan | cases | 0 | 5 | 12 | 12 | 0 |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 |  | MAX | DRO-007
|  | GT pending — T Central | cases | 0 | 5 | 6 | 5 | -1 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | No change ~1.5 months | MAX | DRO-008
|  | GT pending — NT Dehlon | cases | 0 | 5 | 4 | 4 | 0 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | No change ~1.5 months | MAX | DRO-009
|  | GT pending — NT Mullanpur Dakha | cases | 0 | 5 | 9 | 4 | -5 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | No change ~1.5 months | MAX | DRO-010
|  | GT pending — NT Maloud | cases | 0 | 5 | 4 | 4 | 0 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | No change ~1.5 months | MAX | DRO-011
|  | GT pending — T Jagraon | cases | 0 | 5 | 11 | 3 | -8 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  | MAX | DRO-012
|  | GT pending — NT Sidhwan Bet | cases | 0 | 5 | 12 | 3 | -9 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  | MAX | DRO-013
|  | GT pending — T Khanna | cases | 0 | 5 | 7 | 1 | -6 |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 |  | MAX | DRO-014
▣ PRIORITY TASKS — qualitative / assigned tasks
3 | NHAI Package 1 — Ropar–Ludhiana | Amount pending (Rs Cr) | Rs Cr | 0 | 0 |  | 28 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Talwandi Kalan & 3G-1 | MAX | DRO-015
4 | Kabja Karwai (Possession) | Possession actions this week | no. | [6 empty] | In Progress |  | Auto |  |  | Regular monitoring |  | DRO-016
5 | Action vs Kanungo Jaspreet Dhaka | Departmental proceedings status | status | [6 empty] | In Progress |  | Auto |  |  | Confirm status |  | DRO-017
6 | PM Pragati Portal | Pending packages | no. | 0 | 0 |  |  |  |  | In Progress |  | Auto |  |  | Timely submission | MAX | DRO-018

## SDM Samrala
SDM Samrala — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ PRIORITY TASKS — qualitative / assigned tasks
1 | Ludhiana–Ropar Package II | Possession pending (km) | km | 0 | 0 |  | 5 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 5.315 km; arbitration; LA award challenged by NHAI | MAX | SAMR-001
|  | PD reply on HGK draft award — received? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | NHAI conditionally accepted; under consideration |  | SAMR-002
|  | Machhiwara Chat/Collector additional award — issued? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Draft pending final signature; expected next week |  | SAMR-003
2 | Dhulewal Complex | 📊 Dhulewal flood works completed |  |  |  |  | 2 | [7 empty] | of 18 sanctioned at Dhussi Bandh; 16 stalled. Awaiting DC decision to shift to non-MGNREGA funds.
|  | Flood works completed | works | 18 | 18 |  | 2 |  | 11.11% | Pending/Blocked | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 16 halted; Rs97.93L pending DC; shift to non-MGNREGA? | MIN | SAMR-004
3 | Mushqabad / CBG | Mushqabad objections — draft sent? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  |  |  | SAMR-005
4 | Desilting — Mandala DO Letter | Alternate desilting plan submitted? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Village denied road access |  | SAMR-006

## SDM Jagraon
SDM Jagraon — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ PRIORITY TASKS — qualitative / assigned tasks
1 | CBG Akhara | Court case — next date | date |  |  |  | 08.07.2026 |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | Pending in High Court; status report PENDING |  | JAGR-001
2 | Bhundri | Court case — next date | date |  |  |  | 08.07.2026 |  |  | Pending/Blocked |  | Auto | Gov Cell (report) | 05-06-2026 | Pending in High Court |  | JAGR-002
3 | Ludhiana–Bathinda Package II | Follow-up with NHAI done? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  |  |  | JAGR-003
4 | MLA Jagraon Works — 9 Items | Works completed | works | 9 | 9 |  | 1 |  | 11.11% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | Bhundri done; Raikot Rd & Kacha Malak done too | MIN | JAGR-004
|  | Bridge Bardeke–Gagra (Rs664L) — Finance sanction? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Special Assistance Scheme |  | JAGR-005
|  | Waterlogging Kamal Chowk (Rs10.64Cr) — PMIDC funds? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Pending at CEO PMIDC |  | JAGR-006

## SDM Payal
SDM Payal — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ PRIORITY TASKS — qualitative / assigned tasks
1 | Court — Rajgarh / Medical College | Medical College land (acres) | acres |  |  |  | 12.74 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Mutation done; proposal to DC; State surplus land route |  | PAYL-001
|  | Rajgarh — placed before FCR Sahib? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Nothing pending at SDM end |  | PAYL-002
2 | Doraha Cycle Track | Estimate value (Rs Cr) | Rs Cr |  |  |  | 10 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 12 km; XEN Canal Sangrur; final estimate for vetting |  | PAYL-003
3 | Maloud — CSR to DMF | CSR estimate (Rs16L) converted to DMF? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Letter under consideration from DC |  | PAYL-004
4 | Rangla Punjab — Maloud & Doraha | Block Maloud proposals submitted (Rs Cr) | Rs Cr |  |  |  | 1.25 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Submitted to ADC RD |  | PAYL-005
|  | Block Doraha — works completed | works | 17 | 17 |  | 10 |  | 58.82% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 7 ongoing; completion by Jun 2026 | MIN | PAYL-006

## SDM East
SDM East — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ PRIORITY TASKS — qualitative / assigned tasks
1 | Flood — Certificates from XENs | Desilting completion certificate (XEN Drainage)? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Certificates pending; DSI from XEN Mining too |  | EAST-001
2 | Sherpur Chowk | ROW + MC pipeline (Dholewal) resolved? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Consultant being hired by MCL |  | EAST-002
3 | Giaspura to Sherpur — New Drain | DPR submitted / work started? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  |  |  | EAST-003
4 | Ladhowal DPR — Railway UnderBridge | Designer certificate submitted? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  |  |  | EAST-004
5 | MCL Sewer Line | Permission from competent authority? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Proposal pending with RO NHAI |  | EAST-005
6 | Service Road Encroachment | Action on encroachment taken? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Notice issued; copy from Akshat NH |  | EAST-006
7 | Gehlewal School Transfer | Police help for demarcation provided? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Opposition from villagers; DEO letter to SDM East |  | EAST-007
8 | BL Kapoor Hospital | Court case — next hearing date | date |  |  |  | 15.05.2026 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Rebuttal |  | EAST-008
9 | Jail Visit & Land Possession | Jail visit done / possession completed? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Visit done as per demand |  | EAST-009

## SDM West
SDM West — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ PRIORITY TASKS — qualitative / assigned tasks
1 | Southern Bypass — NHAI Matters | SDM West land issues — villages pending | villages | 0 | 0 |  | 16 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | Coordination with CMFO/DRO | MAX | WEST-001
2 | NHAI Delhi–Katra | Gujjarwal — land award pending (ha) | ha | 0 | 0 |  | 0.2546 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | To be done next week | MAX | WEST-002
|  | Dakha 8.25 acres — award done (ha) | ha | 3.34 | 3.34 |  | 1.413 |  | 42.31% | In Progress | 🔴 LOW | Auto | Gov Cell (report) | 05-06-2026 | 3.491 acre done, sent to PD | MIN | WEST-003
|  | Tubewell + Motor compensation — awarded? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | Asset award done this week |  | WEST-004
|  | Missing Khasra (Dakha) resolved? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | From 11 May |  | WEST-005
3 | MLA Dakha Works — 6 Items | Raikot Road Divider (Rs50L) — AA approved? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Safety audit; AA pending |  | WEST-006
|  | SOE Baddowal — education budget released? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Students in corridors; budget awaited |  | WEST-007
|  | Rural link roads — length done (km) | km |  |  |  | 15.78 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | NABARD-30:7.85 + SASCI-100:7.93 done; SASCI-533:38.94 ongoing |  | WEST-008
4 | Weekly SIR Progress Report | SIR weekly report submitted? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | To be submitted regularly |  | WEST-009
5 | KS Sidhu Ji Speaking Order | Compliance status | status | [6 empty] | In Progress |  | Auto |  |  | Confirm compliance |  | WEST-010

## SDM Raikot
SDM Raikot — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ PRIORITY TASKS — qualitative / assigned tasks
1 | NHAI Ldh–Bathinda Pkg 2 | 2.06 km — amount disbursed (Rs Cr) | Rs Cr |  |  |  | 1.5 |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | 1.5 Cr disbursed today |  | RAIK-001
|  | 0.42 km — arbitration cases pending | cases | 0 | 0 |  | 6 |  |  | Pending/Blocked | 🔴 HIGH | Auto | Gov Cell (report) | 05-06-2026 | 9 at Arbitrator Patiala; 3 disposed | MAX | RAIK-002
|  | 1.46 km — award (Village Sarabha draft ready)? (Y/N) | Y/N | [6 empty] | Pending/Blocked |  | Auto |  |  | Chat rate pending Tehsildar Central |  | RAIK-003
|  | 3.06 km — higher compensation demand | status | [6 empty] | In Progress |  | Auto |  |  | Processing |  | RAIK-004
2 | Court Cases — Regular Monitoring | No-representation defaults | no. | 0 | 0 |  |  |  |  | In Progress |  | Auto |  |  | Zero tolerance | MAX | RAIK-005
3 | Mother & Child Hospital Raikot | HR & equipment list — sent to PHSC? (Y/N) | Y/N |  |  |  | Yes |  |  | In Progress |  | Auto | Gov Cell (report) | 05-06-2026 | Sent to higher authorities |  | RAIK-006
4 | Ward Bandi Raikot | Notification done? (Y/N) | Y/N |  |  |  | Yes |  |  | Completed |  | Auto | Gov Cell (report) | 05-06-2026 | No public objection; notified |  | RAIK-007

## RTA
RTA — Priority Agenda Review ¦ DC Ludhiana (MASTER)
Sr | Priority Agenda | KPI / Metric | Concerned Officer / Unit | Target / Total | Flag Bar | Last Value | Current Value | Change | Achieved % | Status | Auto-Flag | Bottom Performer | Updated By | Update Date | Remarks / Context / Pending Action | Rule | Key
▣ PRIORITY TASKS — qualitative / assigned tasks
1 | DL / RC Pendency | DL applications pending | apps | 0 | 0 |  |  |  |  | In Progress |  | Auto |  |  | Action plan required | MAX | RTA-001
|  | RC applications pending | apps | 0 | 0 |  |  |  |  | In Progress |  | Auto |  |  |  | MAX | RTA-002
2 | Safe School Vahan | Challans/warnings to school buses | no. |  |  | 25 |  |  |  | In Progress |  | Auto |  |  | 25 issued last meeting |  | RTA-003
|  | Buses found unfit — action taken | no. | [6 empty] | In Progress |  | Auto |  |  |  |  | RTA-004
3 | VIP Functions | Upcoming functions — arrangements confirmed? (Y/N) | Y/N | [6 empty] | In Progress |  | Auto |  |  | List to be provided |  | RTA-005

## 🔗 Data Connections
DATA CONNECTIONS — linking officer workbooks into this master (Google Sheets)
How it works | Each officer keeps their own Google Sheet workbook. That workbook has a tab called 'MASTER FEED' listing every KPI with a unique Key + live Current / Status / Auto-Flag. This master pulls those values by Key using IMPORTRANGE + VLOOKUP.
One-time setup | 1) Upload each officer workbook to Google Drive and open as a Google Sheet. 2) Copy its URL. 3) In the formulas below, replace <OFFICER_URL> with that URL. 4) Paste the formula into the officer's tab here, in the Current Value (H), Status (K) and Auto-Flag (L) columns of each SCHEME/TASK row. 5) The first time, click the cell → 'Allow access' to authorise the link.
Key column | Every row in this master carries a hidden Key in column R (e.g. ADCG-001). The officer workbook's MASTER FEED uses the same Keys, so values match even if rows are reordered.
FORMULA TEMPLATES (paste into the matching column cell of each scheme/task row)
Current Value (col H)
Status (col K)
Auto-Flag (col L)
Remarks (col P)
OFFICER WORKBOOKS
ADC (G) | Key prefix: ADCG-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
ADC (RD) | Key prefix: ADCRD-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
ADC (UD) | Key prefix: ADCUD-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
ADC (J) | Key prefix: ADCJ-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
ADC (K) | Key prefix: ADCK-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
CMFO | Key prefix: CMFO-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
AC (G) | Key prefix: ACG-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
DRO | Key prefix: DRO-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
SDM Samrala | Key prefix: SAMR-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
SDM Jagraon | Key prefix: JAGR-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
SDM Payal | Key prefix: PAYL-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
SDM East | Key prefix: EAST-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
SDM West | Key prefix: WEST-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
SDM Raikot | Key prefix: RAIK-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.
RTA | Key prefix: RTA-*** ¦ workbook: ✓ built ¦ paste its URL into the templates above for this officer's tab.